## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 5 | 1 | 2 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | COLLEGE FINDER INDIA |  | Project Id: |  | Project Manager: | Harshada Topale |  |  | Assumption | 4 | 0 | 0 | 0 | 1 | 0
[10 empty] | Issue | 5 | 0 | 4 | 0 | 0 | 0
| DOCUMENT VERSION: |  |  | Last Updated date: |  | Project Team Lead: | ABC |  |  | Dependency | 3 | 0 | 1 | 0 | 1 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 17 |  |  |  |  | 10
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
RAID Category | Dependency | Third-party CSS libraries for UI effects. | UI may break if library updates introduce breaking changes. | Lock library versions and test after updates. | Project Owner | Low | N/A | Open | Risk
Risk | Risk | Inability to do required maintenance on time. | Impact on the project schedule and cost. | Schedule regular maintenance slots and set reminders. | Project Owner | High | 18 | Open | Assumption
3 | Risk | Long supply delivery time | Impact on project schedule | Plan ahead and order supplies early. | Project Owner | Critical | 24 | Closed | Issue
4 | Assumption | All required tools and libraries will be available. | Delays if tools are missing. | Verify and install all dependencies before starting. | Project Owner | Medium | N/A | Open | Dependency
5 | Issue | Unexpected bug in the college search feature. | Delays release and affects user experience. | Allocate extra time for debugging and testing. | Project Owner | High | N/A | Open
6 | Dependency | Google Gemini API availability. | Project cannot fetch college data if API is down. | Monitor API status and prepare a fallback message for users. | Project Owner | High | N/A | Open | Open
7 | Risk | Scope creep due to additional feature requests. | Project timeline and budget may be exceeded. | Strict change control process and stick to initial requirements. | Project Owner | Medium | 12 | Open | Closed
8 | Assumption | All required environment variables will be provided before deployment. | Deployment may fail if variables are missing. | Document all required variables and verify before deployment. | Project Owner | Medium | N/A | Open
9 | Issue | Performance issues with large college datasets. | Slow user experience and possible timeouts. | Optimize data processing and implement pagination. | Project Owner | High | N/A | Open | Critical
10 | Issue | Hosting service uptime. | If server downtime occurs, app may be inaccessible. | Choose a reliable hosting provider and set up monitoring. | Project Owner | High | N/A | Open | High
11 | Risk | User data privacy concerns. | Legal and compliance risks if sensitive data is mishandled. | Implement strong encryption and follow privacy guidelines. | Project Owner | Critical | 20 | Open | Moderate
12 | Assumption | Users will have stable internet access. | Users with poor connectivity may face errors. | Provide error handling and retry mechanisms. | Project Owner | Low | N/A | Open | Low
13 | Issue | College logo/images not loading properly. | User interface looks incomplete. | Add fallback images and optimize file handling. | Project Owner | Medium | N/A | Closed | Negligible
14 | Dependency | Browser compatibility. | App may break on outdated browsers. | Perform cross-browser testing and provide polyfills if needed. | Project Owner | Medium | N/A | Open
15 | Risk | Team member unavailability. | Delays in feature delivery. | Have backup resources and redistribute tasks as needed. | Project Owner | High | 10 | Open
16 | Assumption | APIs will return data within acceptable response times. | Slow responses could frustrate users. | Use caching and optimize API queries. | Project Owner | Medium | N/A | Open
17 | Issue | Form validation errors missed. | Incorrect data may be submitted. | Thoroughly test validation logic. | Project Owner | High | N/A | Open
18
19
20
21
22
23
24