## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | COLLEGE FINDER INDIA |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID
PROJECT MANAGER
PROJECT SPONSOR
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
ID | Date | Issue Title | Category | Root Cause | Proposed Solution | Resolution | Assigned To | Status | Lesson Learned
1 | 2025-06-20 | Gemini AI response parsing errors found in early testing | Technical / Implementation | Returned API data was sometimes malformed JSON and not consistent | Introduce fallback prompts with stricter data checks before parsing | Built fallback that retries with simpler prompts if parsing fails | Prachi Jain | COMPLETED | Improved error handling increased overall reliability
2 | 2025-06-25 | UI design progress was slower than planned | Planning / Design | Wireframes were overly detailed, causing timeline delays | Begin with minimal UI drafts and refine using user feedback | Rebuilt interface with a simpler, core-focused design | Prachi Jain | COMPLETED | Simplified layout enhanced usability and speed
3 | 2025-06-30 | College dataset accuracy differed by region | Data / Quality | Some areas returned outdated or incomplete college info | Combine multiple data providers and apply consistency checks | Added validation rules and secondary search fallback | Prachi Jain | COMPLETED | Further data sources needed for stronger coverage
4 | 2025-07-04 | Missing location input validation during early planning | Requirements / Analysis | Validation guidelines for user location input were not specified | Define clear validation rules and include them in test scenarios | Added location validation with error alerts and smart suggestions | Prachi Jain | COMPLETED | Error messages + suggestions improved user satisfaction
5 | 2025-07-10 | Netlify deployment failed due to environment mismatches | Deployment / DevOps | Local builds passed but cloud environment caused issues | Test deployment on hosting platforms earlier and note config needs | Created a deployment guide and fixed Netlify build settings | Prachi Jain | COMPLETED | Early platform testing prevents last-minute blockers